## Cover Sheet
Project Name |  | Guideline Quoting |  |  |  |  | Note: Standardized version numbering convention: Drafts – (Before approval signature) 0.# 0.#+1 0.#+2 Published – (Once there is an approval on the document) 1.0 1.# 1.#+1
Project ID |  | NREQ00000331
Business Unit |  | IT - Application Development
Project Manager |  | Ananthakrishnan ANBALAGAN
Created By |  | Hemraj Solanki
Created Date |  | 2016-07-27
Reviewer |  | Hemanth Kumar BABU
Reviewed Date
Approver |  | Venkatasubramanian NARASIMHAN
Approved Date
Version # |  | 0.1
Document History |  |  | Document Classification | Internal |  | Document ID
Version
Version No. | Nature of modification |  |  | Effective date | Modified By |  | Approved By | Approved Date
0.1 | Guideline Quoting

## List (hidden)
Testing Status | Defect Status | Testing By (List the Name of Testing Team) | Testing Type
Pass | Open |  | Functional
Reject | Fixed |  | Regression
Fail | Rejected |  | UAT
Deffered | On-Hold |  | Performance
Re-Test |  |  | Stress
Ad-Hoc

## Activity
Project Activity Plan
Activity Plan | [6 empty] | Schedule
Project Name | Guideline Quoting
Program Manager | Ananthakrishnan ANBALAGAN
Target
STAGE | Sl.No | MILESTONE |  | Team | Resource | Planned Begin Date | Planned End Date | Revised Start Date | Revised End Date | Actual Start Date | Actual End Date | Status
01. Inititation | 1 | Kick Off | Understand the requirements to setup | Development Team, Process Team and Project Team | Hemraj Solanki | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | completed
02. Requirement Analysis | 2 | Requirement Discussion | Requirement Discussion | Development Team | Hemraj Solanki | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | completed
03.Process Design Stage | 3.01 | Development | Database Planning & Design and Front End logic | Development Team | Hemraj Solanki | 2016-07-27 | 2016-07-28 | 2016-07-27 | 2016-07-28 | 2016-07-27 | 2016-07-28 | completed
| 3.02 | Development | Admin - TAT Info,User Access,Holiday List,Report Points,Productivity,Priority,Region,Request Type,Container Type,Office,Modes,Error Type,Status,Query Type,Error Category. | Development Team | Hemraj Solanki | 2016-07-29 | 2016-08-04 | 2016-08-01 | 2016-08-08 | 2016-08-01 | 2016-08-08 | completed
| 3.03 | Development | Unit Testing | Development Team | Hemraj Solanki | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | completed
| 3.04 | Development | Indexer Form | Development Team | Hemraj Solanki | 2016-08-08 | 2016-08-10 | 2016-08-09 | 2016-08-11 | 2016-08-09 | 2016-08-11 | completed
| 3.05 | Development | Process Queue(Publish Process) | Development Team | Hemraj Solanki | 2016-08-11 | 2016-08-16 | 2016-08-12 | 2016-08-19 | 2016-08-12 | 2016-08-19 | completed
| 3.06 | Development | RFI Queue(Pending In and Pending Out) | Development Team | Hemraj Solanki | 2016-08-17 | 2016-08-19 | 2016-08-22 | 2016-08-24 | 2016-08-22 | 2016-08-24 | completed
| 3.07 | Development | Unit Testing | Development Team | Hemraj Solanki | 2016-08-19 | 2016-08-19 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | completed
| 3.08 | Development | Audit Queue | Development Team | Hemraj Solanki | 2016-08-22 | 2016-08-24 | 2016-08-25 | 2016-08-26 | 2016-08-25 | 2016-08-26 | completed
| 3.09 | Development | Completed Queue | Development Team | Hemraj Solanki | 2016-08-25 | 2016-08-26 | 2016-08-25 | 2016-08-26 | 2016-08-25 | 2016-08-26 | completed
| 3.1 | Delelopment | Quries Sent and Resolution received Mail Trigger | Development Team | Hemraj Solanki | 2016-08-29 | 2016-08-30 | 2016-08-25 | 2016-08-26 | 2016-08-29 | 2016-08-30 | completed
| 3.11 | Development | Unit Testing | Development Team | Hemraj Solanki | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | completed
| 3.12 | Development | Error & CAPA Report | Development Team | Hemraj Solanki | 2016-09-14 | 2016-09-16 | 2016-09-14 | 2016-09-16 | 2016-09-14 | 2016-09-16 | completed
| 3.13 | Development | Daily Report | Development Team | Hemraj Solanki | 2016-09-01 | 2016-09-06 | 2016-09-01 | 2016-09-21 | 2016-09-01 |  | initiated
| 3.14 | Development | Weekly Report | Development Team | Hemraj Solanki | 2016-09-01 | 2016-09-06 | 2016-09-22 | 2016-09-26 |  |  | yet to initiate
| 3.15 | Development | Monthly Report | Development Team | Hemraj Solanki | 2016-09-01 | 2016-09-06 | 2016-09-27 | 2016-09-28 |  |  | yet to initiate
| 3.16 | Development | Productivity Report | Development Team | Hemraj Solanki | 2016-09-07 | 2016-09-12 | 2016-09-28 | 2016-09-29 |  |  | yet to initiate
| 3.17 | Development | Overall Unit Testing | Development Team | Hemraj Solanki | 2016-09-19 | 2016-09-19 | 2016-09-30 | 2016-09-30 |  |  | yet to initiate
| 3.18 | Development | Documentation Part | Developemnt Team | Hemraj Solanki | 2016-09-20 | 2016-09-21 | 2016-10-03 | 2016-10-05 |  |  | yet to initiate
04. Bug Fixes | 4.01 | Development | Defetct Fixes | Development Team | Hemraj Solanki | 2016-09-22 | 2016-09-26 | 2016-10-06 | 2016-10-12 |  |  | yet to initiate