## Shipping+Support
ID | Project | Reporter | Assigned To | Priority | Severity | Reproducibility | Category | Date Submitted | Updated | Summary | Status | Resolution
18608 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P1(high) | minor | always | Defect Request | 06-10-2016 06:32 | 07-10-2016 11:27 | COMM SUP - Guideline quoting - TAT issue in ALL queue | closed | fixed
17572 | Shipping Support | ssc.pmuneeswaran | ssc.pmuneeswaran | P2(medium) | minor | have not tried | Defects | 02-09-2016 09:53 | 07-10-2016 11:19 | Indexed by field is missing in Index screen | closed | fixed
17566 | Shipping Support | ssc.pmuneeswaran | ssc.pmuneeswaran | P2(medium) | minor | have not tried | Defects | 02-09-2016 09:28 | 07-10-2016 10:08 | TAT column colors | closed | fixed
17568 | Shipping Support | ssc.pmuneeswaran | ssc.pmuneeswaran | P2(medium) | minor | always | Defects | 02-09-2016 09:43 | 07-10-2016 10:05 | UPF as popup screen | closed | fixed
17564 | Shipping Support | ssc.pmuneeswaran | ssc.pmuneeswaran | P2(medium) | minor | always | Defects | 02-09-2016 09:19 | 07-10-2016 10:05 | Mail Receiving change clock type | closed | fixed
17565 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P2(medium) | minor | always | Defects | 02-09-2016 09:25 | 07-10-2016 08:46 | Differentiate the Header with body | closed | fixed
17570 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P2(medium) | minor | always | Defects | 02-09-2016 09:49 | 07-10-2016 06:10 | Mark the mandatory fields as '*' | closed | fixed
18641 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P1(high) | minor | always | Defects | 06-10-2016 11:52 | 06-10-2016 11:53 | COMM SUP - Guideline quoting - Reports- All reports- Add lable | assigned | open
18634 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P1(high) | minor | always | Defects | 06-10-2016 10:17 | 06-10-2016 10:18 | COMM SUP - Guideline quoting - Reports- Productivity - Incorrect productivity captured | assigned | open
18631 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P1(high) | minor | always | Defects | 06-10-2016 09:55 | 06-10-2016 09:57 | COMM SUP - Guideline quoting - Reports- All reports- Export Excel | assigned | open
18629 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P2(medium) | minor | always | Defects | 06-10-2016 09:38 | 06-10-2016 09:40 | COMM SUP - Guideline quoting - Reports- CAPA -Wrong Mail received date captured | assigned | open
18627 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P1(high) | minor | always | Defects | 06-10-2016 09:28 | 06-10-2016 09:29 | COMM SUP - Guideline quoting - Reports- All reports- show figure against bar | assigned | open
18625 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P1(high) | minor | always | Defects | 06-10-2016 09:21 | 06-10-2016 09:23 | COMM SUP - Guideline quoting - Reports- All reports- Add scale (# request and Accuracy) | assigned | open
18621 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P1(high) | minor | always | Defects | 06-10-2016 09:10 | 06-10-2016 09:12 | COMM SUP - Guideline quoting - Reports- All reports- Filter option | assigned | open
17569 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P2(medium) | minor | always | Defects | 02-09-2016 09:47 | 06-10-2016 09:02 | change the screen name | closed | fixed
17563 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P2(medium) | minor | always | Defects | 02-09-2016 09:11 | 06-10-2016 09:01 | Index Home screen as create index | closed | fixed
18618 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P2(medium) | minor | always | Defects | 06-10-2016 08:59 | 06-10-2016 09:00 | COMM SUP - Guideline quoting - Reports- All reports- Horizontal scrollbar | assigned | open
18617 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P2(medium) | minor | always | Defects | 06-10-2016 08:55 | 06-10-2016 08:56 | COMM SUP - Guideline quoting - Reports- All reports- Tabular format | assigned | open
17557 | Shipping Support | ssc.pmuneeswaran | EXT.HSOLANKI | P1(high) | minor | always | Defect Request | 02-09-2016 06:27 | 06-10-2016 06:47 | Capital letter not capturing | closed | fixed